## Project Overview
Project Name | Capstone CA 2 |  | Completed | 100%
Date Due | 14th November |  | Est. Hours | 150
Status | On Track |  | Actual Hours | 120 |  |  | Milestone Tracker
[7 empty] | 2023-09-18 | 2023-10-02 | 2023-10-16 | 2023-10-30 | 2023-11-13 | 2023-11-14
Task | Owner | Priority | Est. Time | Act. Time | Status | Milestone | Milestone 1
Schedule Kick off meeting | Group | High | 5 | 5 | Complete |  |  | Milestone 2
Defining Goals | Group | High | 10 | 5 | Complete |  |  |  | Milestone 3
Revising previous work | Group | High | 10 | 6 | Complete |  |  |  |  | Milestone 4
Defining what algorythms to use | Group | Medium | 10 | 10 | Complete | * |  |  |  |  | Milestone 5
ANN fine tuning | Stephen | Medium | 10 | 8 | Complete | [6 empty] | Milestone 6
Random Forest Fine Tuning | Kane | Medium | 10 | 8 | Complete
SVM Application & Fine tuning | Daniel | Medium | 10 | 8 | Complete | *
Choosing Evaluation Metrics | Kane / Stephen | High | 10 | 8 | Complete
Choosing Validation Metrics | Stephen / Daniel | High | 10 | 8 | Complete | *
Reviewing code and results | Group | High | 10 | 8 | Complete
Generating Visuals | Group | Medium | 5 | 5 | Complete | *
Report Structure | Stephen | High | 10 | 8 | Complete
Writing Style | Kane | High | 10 | 8 | Complete
GitHub updates | Daniel | Low | 15 | 12 | Complete | *
Final Review | Group | High | 10 | 8 | Complete
Completion | Group | High | 5 | 5 | Complete | *

## Sprint Meetings
Date | Attendees | Tasks | Date | Attendees | Tasks
2023-09-18 | Kane | Create shared drive for stored files to work off | 2023-11-03 | Kane | Writing Style
| Stephen | Sharing Ca1 code and send around updated notes on tasks |  | Stephen | Report Structure
| Daniel | Pull out Ca1 criteria reviewing X and Y for further discussing |  | Daniel | Branch 1 on Git Hub
Date | Attendees | Tasks | Date | Attendees | Tasks
2023-09-25 | Kane | Set out PM Approach to project tasks | 2023-11-13 | Kane | Final Review of all work
| Stephen | Create Git Hub account and share invites for collaboration |  | Stephen | Final Review of all work
| Daniel | Share updated on Ca1 revision |  | Daniel | Final Review of all work
Date | Attendees | Tasks
2023-10-02 | Kane | Set up Git Hub Account
| Stephen | Set up Git Hub Account
| Daniel | Set up Git Hub Account
Date | Attendees | Tasks
2023-10-11 | Kane | Review Random Frorest model for fine tuning.
| Stephen | Review ANN for fine tuning.
| Daniel | Review SVM for fine tuning.
Date | Attendees | Tasks
2023-10-18 | Kane | Review Evaluation Metrics
| Stephen | Review Evaluation Metrics
| Daniel | Begin to submit commits from Ca1 to Github
Date | Attendees | Tasks
2023-10-27 | Kane | Create Report and PM template in shared drive
| Stephen | Review Validation Metrics
| Daniel | Review Validation Metrics